## Sheet1
Project Name | Status | Acres | Treatment Type | Funding Source | Total Cost | Agreement Type
FUNDED FOREST HEALTH PROJECTS
Looney Stewardship Phase 1 (Layout and Cruise) | Contract Awarded 8/25/18. Work Began 9/10/18. Work Completed 5/17/19. | 893 | Project Layout, Cruise, Roads Package | STF | 125000 | MSA
Looney Stewardship Implementation | Estimated Advertisement Date early Oct 19. Estimated Begin Date TBD. Contract was awarded late fall/early winter - a 3 yr contract. | 893 | Commercial Sale | STF |  | N/A - STF Administered
Twomile | Thinning Completed 9/13/2019. Minor arch site mitigation completed by USFS personnel. | 318 | Shred/Masticate | STF | 168514 | MSA
South 108 | Thinning Completed 9/27/19. | 83 | Mastication | STF | 56517 | MSA
Granite Reforestation | Survival exams will by 9/30/2021 | 402 | Site Prep, Planting, Herbicide Spraying | CalFire | 1132905 | MSA
Granite Thin Phase 1 (Layout & Cruise) | Complete | 2284 | Project Layout, Cruise, Roads, Package | CalFire | 119074 | MSA
Granite Thin Phase 2 (Implementation) | Contract awarded on 5/20; work to begin ASAP. | 1556 | Commercial & Non-Commercial Mechanical Thinning | CalFire | 2046478 | MSA
Strawberry/Phase 2 Rx Fire Prep | Work in place to continue Summit Reforestation's work on hand line installation. | 1000 | Line Construction, Fuel Reduction, Machine & Hand Thinning, Machine Piling. | CalFire | 500000 | MSA
Strawberry/Phase 2 Rx Fire | Fall 2021 burn slated, so as to minimize smoke impacts to communities. | 1,000-3,788 | Broadcast Burning. | STF |  | N/A - STF Administered
Rim Fire Reforestation Phase 3 | Mastication in progress-- contractors on fires right now, but currently work is on/ahead of schedule. | 2000 | Reforestation (ICO, 7'x14', & Founder's Stand Approach) | WCB | 4700000 | MSA
Mt. Lewis Plantation Thinning | ~100/123 acres completed. | 123 | Mastication | STF |  | MSA
WCB Meadows Planning | Field work completed-- planning and design work in progress by Plumas Corps |  |  |  | 200000
CCI Direct Funding | Direct Funding was sought for the SERAL PODS 1-5 and for Murphy Ranch | ~4900 | Fuel Management Features; prescirbed burning; reforestation | CalFire; STF | 7800000
Cold Springs | Survey and layout to begin in coming months | ~3,000 | Fuels Reduction Work | STF | 3400000
PENDING FOREST HEALTH PROPOSALS/PROJECTS
CCI Competitive Funding | Competitive Funding was sought for ~2000 acres of Complex Thin and 600 acres of Reforestation | ~2600 | Thinning; Reforestation | CalFire | 5000000
SNC EA Funding | Due on 9/20/2021, and will fund capacity and grant writing activities | N/A | Capacity | SNC | 300000
FUNDED WILDLIFE HABITAT & WATERSHED RESTORATION PROJECTS
SNC Rim Restoration | Projects Complete. | 225.5 | Deer Habitat (Forest Thinning) 205 ac, 4 Meadows Restored (20.16 ac), 10 Springs Restored (0.05 ac), 2 Culverts Replaced (0.25 ac) | SNC | 817856 | STF-TRT Collection Agreement
WCB Rim Restoration | Projects closing out, one trough still needing to be installed. Final report due by 3/31/2021 | 208 | 24 Meadows Restored (56 acres), Aspen Stand Restoration (33 acres), Deer Habitat Restoration (900 acres), Guzzler & Trough Installation (11), 18 GGO Nest Structures Installed, 2 Culverts Replaced | WCB | 3510000 | STF-TRT Collection Agreement
DFW Rim Fire Watershed Health Improvement Project | Timber Stand Inventory completed, with Mastication RFP to be issued soon. Reforestation and burning tasks are on target. American Forests and the National Forest Foundation will provide complementary funding to purchase seedlings. | 3700 | Reforestation 600 ac, Rx Fire 2,000 ac (400 ac Mastication site prep), Plantation Thinning 1,100 ac | DFW | 3419850 | STF-TRT Collection Agreement
FUNDED CAPACITY GRANTS
DOC Watershed Coordinator Forest Health Grant | Grant Began 08/01/2019. Grant Ends 07/31/2021. | N/A | Develop a plan and/or priorities for restoration treatments in the watershed. Secure Funding. Implement Projects. | Dept of Conservation | 235000 | N/A
SNC Capacity Grant | Grant Began 1/6/2020. Grant Ends March 30, 2022. | N/A | Pilot Project using drone technology for assessment and planning. | SNC | 16283 | N/A
FUNDING SUMMARY
Secured
CalFire (2021) | 5000000
CalFire (2018) | 5000000 |  |  | NFF Grants
SNC (2016) | 1000000 |  |  | 2013-14 | 15888
WCB Rim Habitat Restoration (2015) | 3500000 |  |  | 2014-15 | 28230
WCB Rim Reforestation (2020) | 4700000 |  |  | 2015-16 | 46295
DFW Habitat (2019) | 3500000 |  |  | 2015-16 | 23500
NFF | 223838 |  |  | 2016-17 | 29925
DOC Watershed Coordinator (2019) | 235000 |  |  | 2017-18 | 30000
SNC Capacity | 16000 |  |  | 2018-19 | 25000
Total | 23174838 |  |  | 2019-20 | 25000
|  |  |  | Total | 223838
Pending
OUTCOMES SUMMARY
Acres Treated Under the MSA (Completed or Planned with Funding Secured) |  | 9163
Acres Treated Under other Agreements (Completed or Planned with Funding Secured) |  | 4133.5
Total Acres (Completed or Planned with Funding Secured) |  | 13296.5