## Sheet1
Project Name | Status | Acres | Treatment Type | Funding Source | Total Cost | Agreement Type
FUNDED FOREST HEALTH PROJECTS
Looney Stewardship Phase 1 (Layout and Cruise) | Contract Awarded 8/25/18. Work Began 9/10/18. Work Completed 5/17/19. | 893 | Project Layout, Cruise, Roads Package | STF | 125000 | MSA
Looney Stewardship Implementation | Estimated Advertisement Date early Oct 19. Estimated Begin Date TBD. Contract was awarded late fall/early winter - a 3 yr contract. | 893 | Commercial Sale | STF |  | N/A - STF Administered
Twomile | Thinning Completed 9/13/2019. Minor arch site mitigation completed by USFS personnel. | 318 | Shred/Masticate | STF | 168514 | MSA
South 108 | Thinning Completed 9/27/19. | 83 | Mastication | STF | 56517 | MSA
Granite Reforestation | Complete | 402 | Site Prep, Planting, Herbicide Spraying | CalFire | 1132905 | MSA
Granite Thin Phase 1 (Layout & Cruise) | Complete | 2284 | Project Layout, Cruise, Roads, Package | CalFire | 119074 | MSA
Granite Thin Phase 2 (Implementation) | N/A | 1556 | Commercial & Non-Commercial Mechanical Thinning | CalFire | 2046478 | MSA
Strawberry/Phase 2 Rx Fire Prep | Work in place to continue Summit Reforestation's work on hand line installation. | 1000 | Line Construction, Fuel Reduction, Machine & Hand Thinning, Machine Piling. | CalFire | 500000 | MSA
Strawberry/Phase 2 Rx Fire | To Be burned | 1,000-3,788 | Broadcast Burning. | STF |  | N/A - STF Administered
Rim Fire Reforestation Phase 3 | Mastication and Grapple Piling in progress! Fisher update? | 2000 | Reforestation (ICO, 7'x14', & Founder's Stand Approach) | WCB | 4700000 | MSA
Mt. Lewis Plantation Thinning | Complete | 123 | Mastication | STF |  | MSA
WCB Meadows Planning | Complete |  |  |  | 200000
CCI Direct Funding | RFQ closed; 15 contractors on our list of preferred vendors; ROD to be signed on March 28 and implmentation soon after! | ~4900 | Fuel Management Features; prescirbed burning; reforestation | CalFire; STF | 7800000
Cold Springs | Survey and layout to begin in coming months | ~3,000 | Fuels Reduction Work | STF | 3400000
PENDING FOREST HEALTH PROPOSALS/PROJECTS
CCI Competitive Funding | Competitive Funding was sought for ~2000 acres of Complex Thin and 600 acres of Reforestation | ~2600 | Thinning; Reforestation | CalFire | 5000000
SNC EA Funding | Recommended for Funding | N/A | Capacity | SNC | 380000
SNC EA Funding | Recommended for Funding | N/A | Capacity | SNC | 40000
SNC WF & FR Grant | Application submitted; tentatively favorable feedback, but no recommendations | 2500 | Fuel Management Features | SNCE | 5000000 | MSA
CDFW Prop 1 | Application TBD |  |  |  | 5000000
FUNDED WILDLIFE HABITAT & WATERSHED RESTORATION PROJECTS
SNC Rim Restoration | Projects Complete. | 225.5 | Deer Habitat (Forest Thinning) 205 ac, 4 Meadows Restored (20.16 ac), 10 Springs Restored (0.05 ac), 2 Culverts Replaced (0.25 ac) | SNC | 817856 | STF-TRT Collection Agreement
WCB Rim Restoration | Projects closing out, one trough still needing to be installed. Final report due by 3/31/2021 | 208 | 24 Meadows Restored (56 acres), Aspen Stand Restoration (33 acres), Deer Habitat Restoration (900 acres), Guzzler & Trough Installation (11), 18 GGO Nest Structures Installed, 2 Culverts Replaced | WCB | 3510000 | STF-TRT Collection Agreement
DFW Rim Fire Watershed Health Improvement Project | Reforestation is ongoing; thinning of CDFW units starting, project is progressing! | 3700 | Reforestation 600 ac, Rx Fire 2,000 ac (400 ac Mastication site prep), Plantation Thinning 1,100 ac | DFW | 3419850 | STF-TRT Collection Agreement
FUNDED CAPACITY GRANTS
DOC Watershed Coordinator Forest Health Grant | Complete | N/A | Complete | Dept of Conservation | 235000 | N/A
SNC Capacity Grant | Grant Began 1/6/2020. Grant Ends March 30, 2022. | N/A | Pilot Project using drone technology for assessment and planning. | SNC | 16283 | N/A
FUNDING SUMMARY
Secured
CalFire (2021) | 5000000
CalFire (2018) | 5000000 |  |  | NFF Grants
SNC (2016) | 1000000 |  |  | 2013-14 | 15888
WCB Rim Habitat Restoration (2015) | 3500000 |  |  | 2014-15 | 28230
WCB Rim Reforestation (2020) | 4700000 |  |  | 2015-16 | 46295
DFW Habitat (2019) | 3500000 |  |  | 2015-16 | 23500
NFF | 223838 |  |  | 2016-17 | 29925
DOC Watershed Coordinator (2019) | 235000 |  |  | 2017-18 | 30000
SNC Capacity | 16000 |  |  | 2018-19 | 25000
Total | 23174838 |  |  | 2019-20 | 25000
|  |  |  | Total | 223838
Pending
SNC EA Funding | 300000
SNC EA Funding | 40000
OUTCOMES SUMMARY
Acres Treated Under the MSA (Completed or Planned with Funding Secured) |  | 9163
Acres Treated Under other Agreements (Completed or Planned with Funding Secured) |  | 4133.5
Total Acres (Completed or Planned with Funding Secured) |  | 13296.5